## ULB_Wise_Report_22 October 2026
SNo | ULB Name | Houses Sanctioned | Houses at Foundation | Houses at Lintel | Houses at Roof | Houses Completed | Houses Grounded
8 | Araria, Municipality | 207 | 79 | 26 | 1 | 0 | 106
85 | Forbesganj, Municipality | 109 | 21 | 73 | 8 | 1 | 104
121 | JOGABANI, MUNICIPALITY | 659 | 108 | 437 | 31 | 2 | 586
122 | Jokihat, Town Panchayat | 249 | 12 | 212 | 1 | 1 | 239
181 | NARPATGANJ, TOWN PANCHAYAT | 543 | 175 | 309 | 1 | 0 | 490
211 | Raniganj, Town Panchayat | 732 | 359 | 114 | 0 | 0 | 593
11 | Arwal, Municipality | 229 | 34 | 59 | 25 | 3 | 121
146 | Kurtha, Town Panchayat | 42 | 12 | 28 | 2 | 0 | 42
14 | Aurangabad, Municipality | 221 | 20 | 141 | 51 | 0 | 213
35 | Barun, Town Panchayat | 604 | 119 | 223 | 14 | 0 | 356
71 | DAUDNAGAR, MUNICIPALITY | 1309 | 47 | 1076 | 6 | 0 | 1132
73 | Deo, Town Panchayat | 161 | 20 | 116 | 2 | 0 | 138
178 | Nabinagar, Town Panchayat | 283 | 74 | 63 | 2 | 0 | 139
205 | Rafiganj, Town Panchayat | 36 | 2 | 23 | 10 | 1 | 36
4 | Amarpur, Town Panchayat | 468 | 174 | 100 | 12 | 0 | 291
25 | BANKA, MUNICIPALITY | 312 | 120 | 164 | 25 | 0 | 309
58 | Bounsi, Town Panchayat | 596 | 40 | 439 | 48 | 0 | 529
131 | Katoria, Town Panchayat | 395 | 33 | 355 | 1 | 0 | 391
20 | Bakhri, Municipality | 1845 | 285 | 678 | 9 | 0 | 1054
22 | Balia, Municipality | 268 | 27 | 48 | 0 | 0 | 75
30 | Barauni, Municipality | 557 | 2 | 457 | 0 | 0 | 472
38 | BEGUSARAI, MUNICIPAL CORPORATION | 1507 | 403 | 593 | 67 | 0 | 1113
51 | Bihat, Municipality | 1933 | 335 | 851 | 124 | 2 | 1733
253 | Teghra, Town Panchayat | 458 | 94 | 273 | 20 | 0 | 398
1 | AKBARNAGAR, TOWN PANCHAYAT | 420 | 63 | 230 | 51 | 0 | 350
46 | Bhagalpur, Municipal Corporation | 547 | 138 | 359 | 16 | 0 | 516
97 | Habibpur, Town Panchayat | 745 | 89 | 371 | 139 | 0 | 602
123 | Kahalgaon, Town Panchayat | 245 | 16 | 96 | 74 | 0 | 188
184 | Naugachhia, Municipality | 386 | 41 | 111 | 22 | 2 | 199
202 | Pirpainti, Town Panchayat | 342 | 50 | 219 | 15 | 0 | 284
217 | Sabour, Town Panchayat | 234 | 38 | 121 | 13 | 0 | 172
247 | Sultanganj, Municipality | 167 | 30 | 95 | 21 | 0 | 153
10 | Arrah, Municipal Corporation | 161 | 24 | 123 | 5 | 1 | 153
39 | Behea, Town Panchayat | 230 | 22 | 169 | 10 | 8 | 210
86 | Garhani, Town Panchayat | 1186 | 176 | 549 | 93 | 0 | 821
110 | Jagdishpur, Town Panchayat | 521 | 35 | 149 | 19 | 1 | 233
140 | Koilwar, Town Panchayat | 206 | 27 | 120 | 19 | 0 | 168
201 | Piro, Municipality | 325 | 63 | 94 | 28 | 0 | 187
229 | Shahpur, Town Panchayat | 94 | 17 | 51 | 16 | 5 | 90
59 | Brahmpur, Town Panchayat | 246 | 8 | 218 | 11 | 0 | 237
60 | BUXAR, MUNICIPALITY | 348 | 73 | 206 | 13 | 0 | 305
66 | Chausa, Town Panchayat | 212 | 65 | 118 | 1 | 0 | 185
80 | Dumraon, Municipality | 372 | 39 | 280 | 17 | 4 | 341
109 | Itarhi, Town Panchayat | 409 | 133 | 142 | 5 | 0 | 295
17 | Baheri, Town Panchayat | 316 | 75 | 189 | 0 | 0 | 304
43 | Benipur, Municipality | 802 | 292 | 225 | 5 | 0 | 651
47 | Bharwara, Town Panchayat | 792 | 68 | 408 | 47 | 0 | 535
55 | Biraul, Town Panchayat | 838 | 528 | 17 | 8 | 0 | 662
70 | Darbhanga, Municipal Corporation | 950 | 343 | 387 | 69 | 6 | 806
88 | GHANSHYAMPUR, TOWN PANCHAYAT | 1443 | 330 | 211 | 0 | 0 | 565
104 | HAYAGHAT, Town Panchayat | 400 | 76 | 164 | 11 | 0 | 294
112 | Jale, Town Panchayat | 2545 | 213 | 1840 | 103 | 13 | 2230
125 | KAMTAUL Ahiyari, Town Panchayat | 875 | 158 | 344 | 4 | 0 | 755
147 | KUSHESWAR ASTHAN EAST, Town Panchayat | 621 | 214 | 93 | 62 | 0 | 420
240 | SINGHWARA, Town Panchayat | 1094 | 222 | 678 | 12 | 0 | 913
57 | Bodh Gaya, Municipality | 4137 | 691 | 1008 | 133 | 0 | 1956
79 | Dobhi, Town Panchayat | 649 | 396 | 36 | 0 | 0 | 436
83 | Fatehpur, Town Panchayat | 650 | 52 | 330 | 53 | 0 | 501
87 | Gaya, Municipal Corporation | 1471 | 68 | 1129 | 17 | 11 | 1227
107 | Imamganj, Town Panchayat | 1532 | 59 | 551 | 2 | 0 | 616
135 | Khizarsarai, Town Panchayat | 458 | 126 | 295 | 12 | 1 | 436
233 | Sherghati, Municipality | 841 | 190 | 212 | 18 | 0 | 424
255 | Tikari, Municipality | 403 | 68 | 312 | 3 | 0 | 384
259 | Wazirganj, Town Panchayat | 447 | 313 | 8 | 0 | 0 | 361
29 | BARAULI, MUNICIPALITY | 202 | 132 | 28 | 5 | 0 | 177
93 | Gopalganj, Municipality | 212 | 141 | 56 | 2 | 0 | 202
102 | Hathua, Town Panchayat | 168 | 101 | 33 | 0 | 0 | 145
129 | Kataiya, Town Panchayat | 690 | 71 | 441 | 11 | 7 | 574
167 | MIRGANJ, MUNICIPALITY | 2081 | 356 | 532 | 6 | 0 | 899
114 | Jamui, Municipality | 141 | 48 | 57 | 1 | 2 | 109
119 | Jhajha, Municipality | 876 | 41 | 649 | 30 | 2 | 723
234 | Sikandra, Town Panchayat | 125 | 9 | 102 | 1 | 0 | 112
90 | Ghoshi, Town Panchayat | 1441 | 294 | 507 | 20 | 0 | 852
118 | Jehanabad, Municipality | 338 | 64 | 175 | 17 | 1 | 258
124 | KAKO, Town Panchayat | 233 | 93 | 88 | 0 | 0 | 185
158 | Makhdumpur, Town Panchayat | 938 | 360 | 364 | 33 | 4 | 763
45 | Bhabua, Municipality | 346 | 116 | 162 | 14 | 0 | 299
101 | HATA, TOWN PANCHAYAT | 504 | 167 | 280 | 2 | 0 | 466
143 | Kudra, Town Panchayat | 228 | 16 | 184 | 7 | 0 | 209
169 | Mohania, Town Panchayat | 210 | 21 | 136 | 14 | 1 | 175
209 | Ramgarh, Town Panchayat | 170 | 4 | 138 | 3 | 0 | 145
5 | AMDABAD, Town Panchayat | 377 | 59 | 308 | 0 | 0 | 367
23 | BALRAMPUR, TOWN PANCHAYAT | 108 | 42 | 53 | 8 | 0 | 107
28 | BARARI, Town Panchayat | 297 | 152 | 77 | 2 | 0 | 232
34 | Barsoi, Town Panchayat | 74 | 34 | 14 | 4 | 1 | 56
130 | Katihar, Municipal Corporation | 664 | 229 | 370 | 51 | 0 | 650
142 | KORHA, TOWN PANCHAYAT | 317 | 75 | 195 | 0 | 0 | 279
145 | Kursela, Town Panchayat | 228 | 81 | 110 | 21 | 0 | 212
160 | Manihari, Town Panchayat | 148 | 76 | 36 | 0 | 0 | 112
3 | Alauli, Town Panchayat | 611 | 121 | 404 | 0 | 0 | 527
40 | Beldaur, Town Panchayat | 320 | 12 | 296 | 1 | 0 | 310
92 | Gogri Jamalpur, Municipality | 1128 | 231 | 737 | 24 | 7 | 1042
133 | Khagaria, Municipality | 239 | 71 | 130 | 2 | 0 | 204
162 | Mansi, Town Panchayat | 409 | 69 | 227 | 20 | 0 | 317
192 | Parbatta, Town Panchayat | 867 | 36 | 721 | 2 | 0 | 759
16 | Bahadurganj, Town Panchayat | 363 | 76 | 232 | 8 | 0 | 333
137 | Kishanganj, Municipality | 325 | 41 | 57 | 4 | 0 | 102
196 | Pauakhali, Town Panchayat | 1345 | 843 | 267 | 15 | 0 | 1142
254 | Thakurganj, Town Panchayat | 400 | 125 | 131 | 39 | 1 | 314
27 | BARAHIYA, MUNICIPALITY | 197 | 44 | 93 | 27 | 0 | 165
148 | Lakhisarai, Municipality | 916 | 172 | 438 | 38 | 0 | 663
250 | Suryagadha, Municipality | 559 | 45 | 437 | 20 | 0 | 507
2 | Alamnagar, Town Panchayat | 2023 | 48 | 493 | 4 | 0 | 600
49 | Bihariganj, Town Panchayat | 1648 | 340 | 290 | 0 | 0 | 652
151 | Madhepura, Municipality | 1254 | 148 | 76 | 4 | 0 | 232
175 | Murliganj, Town Panchayat | 165 | 31 | 92 | 5 | 0 | 128
238 | SINGHESHWAR, TOWN PANCHAYAT | 506 | 135 | 319 | 0 | 0 | 455
257 | Udakishunganj, Municipality | 3794 | 1596 | 1867 | 24 | 0 | 3658
42 | Benipatti, Town Panchayat | 541 | 10 | 390 | 39 | 0 | 440
89 | Ghoghardiha, Town Panchayat | 160 | 85 | 52 | 7 | 0 | 332
111 | Jainagar, Town Panchayat | 358 | 55 | 134 | 35 | 0 | 256
120 | Jhanjharpur, Municipality | 639 | 74 | 357 | 19 | 11 | 554
153 | Madhubani, Municipal Corporation | 2417 | 96 | 497 | 25 | 1 | 619
198 | Phulparas, Town Panchayat | 1145 | 170 | 717 | 26 | 0 | 975
12 | Asarganj, Town Panchayat | 161 | 15 | 111 | 23 | 0 | 149
103 | Haweli Kharagpur, Municipality | 320 | 64 | 192 | 10 | 0 | 274
113 | JAMALPUR, MUNICIPALITY | 161 | 35 | 71 | 46 | 9 | 162
173 | MUNGER, MUNICIPAL CORPORATION | 301 | 64 | 197 | 12 | 16 | 292
223 | Sangrampur, Town Panchayat | 326 | 103 | 157 | 5 | 0 | 285
252 | Tarapur, Town Panchayat | 352 | 32 | 262 | 43 | 0 | 338
36 | BARURAAJ, TOWN PANCHAYAT | 814 | 272 | 359 | 15 | 2 | 752
126 | Kanti, Municipality | 339 | 65 | 179 | 9 | 0 | 258
144 | Kurhani, Town Panchayat | 431 | 100 | 156 | 0 | 0 | 278
152 | Madhopur Susta, Town Panchayat | 685 | 250 | 276 | 5 | 0 | 589
166 | MINAPUR, TOWN PANCHAYAT | 858 | 154 | 545 | 19 | 1 | 725
172 | Motipur, Municipality | 1051 | 214 | 594 | 33 | 25 | 940
174 | MURAUL, TOWN PANCHAYAT | 200 | 23 | 145 | 13 | 0 | 181
177 | Muzaffarpur, Municipal Corporation | 350 | 56 | 147 | 30 | 0 | 235
219 | Sahebganj, Municipality | 629 | 155 | 262 | 14 | 0 | 440
220 | Sakra, Town Panchayat | 545 | 127 | 235 | 43 | 3 | 420
225 | Saraiya, Town Panchayat | 512 | 23 | 384 | 4 | 0 | 412
13 | Asthawan, Town Panchayat | 865 | 65 | 663 | 12 | 0 | 741
50 | Biharsharif, Municipal Corporation | 720 | 249 | 387 | 1 | 0 | 637
63 | Chandi, Town Panchayat | 85 | 39 | 46 | 0 | 0 | 85
81 | Ekangarsarai, Town Panchayat | 35 | 23 | 10 | 1 | 0 | 34
91 | Giriak, Town Panchayat | 333 | 164 | 35 | 2 | 0 | 220
99 | Harnaut, Town Panchayat | 260 | 25 | 140 | 0 | 0 | 168
105 | Hilsa, Municipality | 218 | 42 | 154 | 21 | 3 | 232
108 | Islampur, Municipality | 56 | 8 | 37 | 9 | 0 | 54
179 | Nalanda, Town Panchayat | 572 | 88 | 405 | 19 | 0 | 519
191 | Parbalpur, Town Panchayat | 46 | 9 | 33 | 0 | 0 | 42
197 | Pawapuri, Town Panchayat | 648 | 80 | 321 | 63 | 0 | 472
206 | Rahui, Town Panchayat | 399 | 78 | 293 | 0 | 0 | 371
208 | Rajgir, Town Panchayat | 99 | 4 | 56 | 29 | 0 | 89
226 | SARMERA, TOWN PANCHAYAT | 135 | 5 | 80 | 15 | 0 | 102
235 | Silao, Town Panchayat | 254 | 22 | 113 | 39 | 9 | 184
106 | Hisua, Town Panchayat | 750 | 690 | 43 | 9 | 0 | 743
186 | Nawada, Municipality | 809 | 191 | 344 | 139 | 5 | 681
207 | Rajauli, Town Panchayat | 533 | 140 | 283 | 21 | 0 | 460
258 | Warisaliganj, Town Panchayat | 270 | 59 | 66 | 63 | 1 | 195
15 | Bagaha, Municipality | 815 | 69 | 516 | 10 | 80 | 677
44 | Bettiah, Municipal Corporation | 508 | 147 | 151 | 21 | 0 | 321
64 | Chanpatia, Town Panchayat | 170 | 54 | 81 | 14 | 0 | 154
150 | Lauria, Town Panchayat | 524 | 192 | 162 | 13 | 0 | 393
180 | Narkatiaganj, Municipality | 82 | 27 | 40 | 2 | 0 | 70
210 | Ramnagar, Town Panchayat | 1570 | 415 | 735 | 25 | 0 | 1354
260 | Yogapatti, Town Panchayat | 415 | 19 | 354 | 17 | 0 | 393
21 | Bakhtiyarpur, Municipality | 179 | 88 | 28 | 1 | 0 | 117
32 | Barh, Municipality | 118 | 27 | 62 | 16 | 0 | 115
52 | Bihta, Municipality | 816 | 523 | 250 | 2 | 0 | 782
53 | Bikram, Town Panchayat | 179 | 39 | 76 | 11 | 3 | 129
77 | Dinapur Nizamat, Municipality | 131 | 22 | 83 | 21 | 0 | 129
84 | Fatwah, Municipality | 524 | 129 | 281 | 18 | 0 | 446
134 | Khagaul, Municipality | 63 | 18 | 23 | 15 | 0 | 59
136 | Khusrupur, Town Panchayat | 224 | 12 | 87 | 9 | 0 | 108
159 | Maner, Town Panchayat | 445 | 104 | 111 | 15 | 0 | 233
164 | Masaurhi, Municipality | 523 | 173 | 255 | 13 | 0 | 446
170 | Mokameh, Municipality | 126 | 9 | 11 | 3 | 0 | 24
183 | Naubatpur, Town Panchayat | 515 | 178 | 288 | 23 | 0 | 496
190 | Paliganj, Town Panchayat | 107 | 20 | 65 | 2 | 0 | 88
195 | Patna Municipal Corporation | 72 | 10 | 40 | 22 | 0 | 72
199 | Phulwari Sharif, Municipality | 64 | 20 | 37 | 3 | 1 | 61
203 | Punpun, Town Panchayat | 352 | 137 | 147 | 0 | 0 | 303
222 | SAMPATCHAK, MUNICIPALITY | 124 | 24 | 47 | 49 | 0 | 122
9 | Areraj, Town Panchayat | 329 | 118 | 116 | 37 | 0 | 272
61 | Chakia, Municipality | 1188 | 2 | 133 | 10 | 0 | 146
74 | Dhaka, Municipality | 135 | 223 | 72 | 9 | 8 | 688
132 | Kesaria, Town Panchayat | 200 | 58 | 96 | 24 | 0 | 181
171 | Motihari, Municipal Corporation | 1958 | 970 | 399 | 18 | 0 | 1664
212 | Raxaul Bazar, Municipality | 423 | 200 | 152 | 43 | 0 | 426
246 | Sugauli, Town Panchayat | 307 | 86 | 160 | 1 | 10 | 268
6 | Amour, Town Panchayat | 815 | 258 | 408 | 32 | 0 | 708
19 | Baisi, Town Panchayat | 717 | 65 | 398 | 233 | 0 | 698
26 | Banmankhi Bazar, Municipality | 1397 | 66 | 156 | 0 | 0 | 228
48 | Bhawanipur, Town Panchayat | 347 | 90 | 148 | 0 | 0 | 240
62 | CHAMPANAGAR, TOWN PANCHAYAT | 529 | 104 | 353 | 0 | 0 | 458
75 | Dhamdaha, Town Panchayat | 664 | 112 | 345 | 4 | 0 | 473
117 | Jankinagar, Town Panchayat | 1360 | 654 | 272 | 0 | 0 | 1072
128 | KASBA, TOWN PANCHAYAT | 316 | 32 | 59 | 7 | 0 | 102
168 | MIRGANJ, TOWN PANCHAYAT | 512 | 159 | 260 | 11 | 0 | 437
204 | Purnia, Municipal Corporation | 1851 | 332 | 1041 | 50 | 31 | 1495
216 | Rupauli, Town Panchayat | 750 | 244 | 321 | 2 | 0 | 581
54 | Bikramganj, Municipality | 120 | 22 | 63 | 25 | 0 | 112
67 | Chenari, Town Panchayat | 376 | 15 | 322 | 14 | 0 | 354
72 | Dehri Dalmianagar, Municipality | 619 | 119 | 314 | 23 | 0 | 458
78 | DINARA, TOWN PANCHAYAT | 203 | 27 | 144 | 2 | 0 | 177
127 | KARAKAT, TOWN PANCHAYAT | 453 | 68 | 301 | 0 | 0 | 381
138 | Koath, Town Panchayat | 323 | 63 | 129 | 78 | 21 | 294
139 | Kochas, Town Panchayat | 61 | 2 | 0 | 0 | 0 | 2
182 | Nasriganj, Town Panchayat | 154 | 78 | 38 | 0 | 0 | 125
188 | Nokha, Municipality | 2328 | 778 | 568 | 10 | 0 | 1477
214 | ROHTAS, Town Panchayat | 494 | 146 | 176 | 11 | 0 | 333
227 | Sasaram, Municipal Corporation | 1722 | 505 | 1056 | 12 | 0 | 1604
24 | Bangaon, Town Panchayat | 1310 | 339 | 917 | 2 | 0 | 1355
185 | Nauhatta, Town Panchayat | 1401 | 663 | 478 | 0 | 0 | 1203
218 | Saharsa, Municipal Corporation | 5224 | 1339 | 3701 | 3 | 57 | 5109
237 | Simri Bakhtiyarpur, Town Panchayat | 1902 | 722 | 962 | 41 | 0 | 1735
243 | Sonbarsa, Town Panchayat | 916 | 137 | 624 | 26 | 0 | 811
245 | SOUR BAZAR, TOWN PANCHAYAT | 1626 | 6 | 944 | 4 | 0 | 1517
69 | Dalsinghsarai, Municipality | 1376 | 405 | 323 | 1 | 0 | 797
176 | MUSRI GHARARI, TOWN PANCHAYAT | 1569 | 41 | 474 | 138 | 0 | 655
215 | ROSERA, MUNICIPALITY | 889 | 86 | 109 | 46 | 1 | 249
221 | Samastipur, Municipal Corporation | 1758 | 258 | 1138 | 34 | 4 | 1726
224 | Sarairanjan, Town Panchayat | 1309 | 274 | 598 | 192 | 1 | 1117
228 | SHAHPUR PATORI, MUNICIPALITY | 2220 | 534 | 1298 | 5 | 0 | 2033
239 | Singhia, Town Panchayat | 1075 | 63 | 822 | 11 | 0 | 901
251 | Tajpur, Municipality | 1097 | 135 | 506 | 44 | 0 | 781
65 | Chapra, Municipal Corporation | 807 | 195 | 404 | 7 | 0 | 667
76 | Dighwara, Town Panchayat | 525 | 128 | 44 | 8 | 0 | 199
82 | Ekma Bazar, Town Panchayat | 561 | 155 | 221 | 37 | 0 | 421
141 | KOPA, TOWN PANCHAYAT | 20 | 10 | 6 | 0 | 0 | 16
161 | Manjhi, Town Panchayat | 671 | 365 | 48 | 1 | 2 | 519
163 | Marhaura, Town Panchayat | 768 | 196 | 323 | 9 | 0 | 710
165 | Mashrakh, Town Panchayat | 494 | 90 | 308 | 12 | 0 | 411
193 | Parsa Bazar, Town Panchayat | 1092 | 385 | 525 | 35 | 1 | 1015
213 | Revelganj, Town Panchayat | 277 | 60 | 101 | 23 | 0 | 198
244 | Sonepur, Town Panchayat | 100 | 17 | 60 | 8 | 1 | 87
31 | Barbigha, Municipality | 436 | 52 | 282 | 32 | 0 | 370
68 | Chewara, Town Panchayat | 181 | 13 | 85 | 0 | 0 | 98
230 | Sheikhopur Sarai, Town Panchayat | 245 | 102 | 80 | 8 | 0 | 191
231 | Sheikhpura, Municipality | 632 | 199 | 273 | 29 | 0 | 510
232 | Sheohar, Town Panchayat | 239 | 30 | 178 | 0 | 0 | 208
18 | Bairgania, Municipality | 1449 | 330 | 274 | 1 | 1 | 627
41 | Belsand, Town Panchayat | 951 | 131 | 270 | 6 | 1 | 411
115 | JANAKPUR ROAD, MUNICIPALITY | 2256 | 505 | 1057 | 549 | 83 | 2205
241 | Sitamarhi, Municipal Corporation | 3691 | 600 | 916 | 2 | 0 | 1518
249 | Sursand, Town Panchayat | 1416 | 61 | 210 | 13 | 0 | 307
7 | Andar, Town Panchayat | 107 | 19 | 53 | 0 | 0 | 72
33 | Barharia, Town Panchayat | 294 | 27 | 220 | 10 | 0 | 281
37 | Basantpur, Town Panchayat | 187 | 106 | 69 | 0 | 0 | 178
94 | Gopalpur, Town Panchayat | 262 | 215 | 7 | 0 | 0 | 248
96 | Guthani, Town Panchayat | 430 | 40 | 268 | 0 | 0 | 311
100 | Hasanpura, Town Panchayat | 261 | 64 | 136 | 0 | 0 | 200
154 | Maharajganj, Town Panchayat | 240 | 20 | 84 | 0 | 0 | 117
157 | Mairwa, Town Panchayat | 201 | 39 | 77 | 2 | 0 | 162
242 | Siwan, Municipality | 3275 | 1611 | 1372 | 124 | 0 | 3169
56 | Birpur, Town Panchayat | 213 | 34 | 65 | 4 | 0 | 104
187 | Nirmali, Town Panchayat | 236 | 79 | 74 | 1 | 0 | 156
200 | Pipra, Town Panchayat | 647 | 187 | 268 | 0 | 0 | 487
236 | Simrahi, Town Panchayat | 659 | 343 | 62 | 10 | 0 | 442
248 | Supaul, Municipality | 275 | 53 | 132 | 11 | 0 | 198
256 | TRIBENIGANJ, MUNICIPALITY | 1621 | 463 | 798 | 7 | 0 | 1335
95 | Goraul, Town Panchayat | 812 | 37 | 473 | 17 | 1 | 541
98 | Hajipur, Municipality | 1708 | 583 | 746 | 12 | 5 | 1480
116 | Jandaha, Town Panchayat | 1092 | 437 | 171 | 0 | 0 | 702
149 | Lalganj, Municipality | 303 | 66 | 111 | 34 | 0 | 214
155 | Mahnar Bazar, Municipality | 60 | 11 | 43 | 2 | 1 | 60
156 | Mahua, Municipality | 929 | 126 | 274 | 81 | 0 | 481
194 | Patepur, Town Panchayat | 693 | 265 | 325 | 24 | 1 | 624
| Total | 175235 | 40916 | 77763 | 5661 | 488 | 131963

## Sheet4
AKBARNAGAR, TOWN PANCHAYAT | 420
ALAMNAGAR, TOWN PANCHAYAT | 2023
ALAULI, TOWN PANCHAYAT | 611
AMARPUR, TOWN PANCHAYAT | 468
AMDABAD, TOWN PANCHAYAT | 377
AMOUR, TOWN PANCHAYAT | 815
ANDAR, TOWN PANCHAYAT | 107
ARARIA, MUNICIPALITY | 207
ARERAJ, TOWN PANCHAYAT | 329
ARRAH, MUNICIPAL CORPORATION | 161
ARWAL, MUNICIPALITY | 229
ASARGANJ, TOWN PANCHAYAT | 161
ASTHAWAN, TOWN PANCHAYAT | 865
AURANGABAD, MUNICIPALITY | 221
BAGAHA, MUNICIPALITY | 815
BAHADURGANJ, TOWN PANCHAYAT | 363
BAHERI, TOWN PANCHAYAT | 316
BAIRGANIA, MUNICIPALITY | 1449
BAISI, TOWN PANCHAYAT | 717
BAKHRI, MUNICIPALITY | 1845
BAKHTIYARPUR, MUNICIPALITY | 179
BALIA, MUNICIPALITY | 268
BALRAMPUR, TOWN PANCHAYAT | 108
BANGAON, TOWN PANCHAYAT | 1310
BANKA, MUNICIPALITY | 312
BANMANKHI BAZAR, MUNICIPALITY | 1397
BARAHIYA, MUNICIPALITY | 197
BARARI, TOWN PANCHAYAT | 297
BARAULI, MUNICIPALITY | 202
BARAUNI, MUNICIPALITY | 557
BARBIGHA, MUNICIPALITY | 436
BARH, MUNICIPALITY | 118
BARHARIA, TOWN PANCHAYAT | 294
BARSOI, TOWN PANCHAYAT | 74
BARUN, TOWN PANCHAYAT | 604
BARURAAJ, TOWN PANCHAYAT | 814
BASANTPUR, TOWN PANCHAYAT | 187
BEGUSARAI, MUNICIPAL CORPORATION | 1507
BEHEA, TOWN PANCHAYAT | 230
BELDAUR, TOWN PANCHAYAT | 320
BELSAND, TOWN PANCHAYAT | 951
BENIPATTI, TOWN PANCHAYAT | 541
BENIPUR, MUNICIPALITY | 802
BETTIAH, MUNICIPAL CORPORATION | 508
BHABUA, MUNICIPALITY | 346
BHAGALPUR, MUNICIPAL CORPORATION | 547
BHARWARA, TOWN PANCHAYAT | 792
BHAWANIPUR, TOWN PANCHAYAT | 347
BIHARIGANJ, TOWN PANCHAYAT | 1648
BIHARSHARIF, MUNICIPAL CORPORATION | 720
BIHAT, MUNICIPALITY | 1933
BIHTA, MUNICIPALITY | 816
BIKRAM, TOWN PANCHAYAT | 179
BIKRAMGANJ, MUNICIPALITY | 120
BIRAUL, TOWN PANCHAYAT | 838
BIRPUR, TOWN PANCHAYAT | 213
BODH GAYA, MUNICIPALITY | 4137
BOUNSI, TOWN PANCHAYAT | 596
BRAHMPUR, TOWN PANCHAYAT | 246
BUXAR, MUNICIPALITY | 348
CHAKIA, MUNICIPALITY | 1188
CHAMPANAGAR, TOWN PANCHAYAT | 529
CHANDI, TOWN PANCHAYAT | 85
CHANPATIA, TOWN PANCHAYAT | 170
CHAPRA, MUNICIPAL CORPORATION | 807
CHAUSA, TOWN PANCHAYAT | 212
CHENARI, TOWN PANCHAYAT | 376
CHEWARA, TOWN PANCHAYAT | 181
DALSINGHSARAI, MUNICIPALITY | 1376
DARBHANGA, MUNICIPAL CORPORATION | 950
DAUDNAGAR, MUNICIPALITY | 1309
DEHRI DALMIANAGAR, MUNICIPALITY | 619
DEO, TOWN PANCHAYAT | 161
DHAKA, MUNICIPALITY | 135
DHAMDAHA, TOWN PANCHAYAT | 664
DIGHWARA, TOWN PANCHAYAT | 525
DINAPUR NIZAMAT, MUNICIPALITY | 131
DINARA, TOWN PANCHAYAT | 203
DOBHI, TOWN PANCHAYAT | 649
DUMRAON, MUNICIPALITY | 372
EKANGARSARAI, TOWN PANCHAYAT | 35
EKMA BAZAR, TOWN PANCHAYAT | 561
FATEHPUR, TOWN PANCHAYAT | 650
FATWAH, MUNICIPALITY | 524
FORBESGANJ, MUNICIPALITY | 109
GARHANI, TOWN PANCHAYAT | 1186
GAYA, MUNICIPAL CORPORATION | 1471
GHANSHYAMPUR, TOWN PANCHAYAT | 1443
GHOGHARDIHA, TOWN PANCHAYAT | 160
GHOSHI, TOWN PANCHAYAT | 1441
GIRIAK, TOWN PANCHAYAT | 333
GOGRI JAMALPUR, MUNICIPALITY | 1128
GOPALGANJ, MUNICIPALITY | 212
GOPALPUR, TOWN PANCHAYAT | 262
GORAUL, TOWN PANCHAYAT | 812
GUTHANI, TOWN PANCHAYAT | 430
HABIBPUR, TOWN PANCHAYAT | 745
HAJIPUR, MUNICIPALITY | 1708
HARNAUT, TOWN PANCHAYAT | 260
HASANPURA, TOWN PANCHAYAT | 261
HATA, TOWN PANCHAYAT | 504
HATHUA, TOWN PANCHAYAT | 168
HAWELI KHARAGPUR, MUNICIPALITY | 320
HAYAGHAT, TOWN PANCHAYAT | 400
HILSA, MUNICIPALITY | 218
HISUA, TOWN PANCHAYAT | 750
IMAMGANJ, TOWN PANCHAYAT | 1532
ISLAMPUR, MUNICIPALITY | 56
ITARHI, TOWN PANCHAYAT | 409
JAGDISHPUR, TOWN PANCHAYAT | 521
JAINAGAR, TOWN PANCHAYAT | 358
JALE, TOWN PANCHAYAT | 2545
JAMALPUR, MUNICIPALITY | 161
JAMUI, MUNICIPALITY | 141
JANAKPUR ROAD, MUNICIPALITY | 2256
JANDAHA, TOWN PANCHAYAT | 1092
JANKINAGAR, TOWN PANCHAYAT | 1360
JEHANABAD, MUNICIPALITY | 338
JHAJHA, MUNICIPALITY | 876
JHANJHARPUR, MUNICIPALITY | 639
JOGABANI, MUNICIPALITY | 659
JOKIHAT, TOWN PANCHAYAT | 249
KAHALGAON, TOWN PANCHAYAT | 245
KAKO, TOWN PANCHAYAT | 233
KAMTAUL AHIYARI, TOWN PANCHAYAT | 875
KANTI, MUNICIPALITY | 339
KARAKAT, TOWN PANCHAYAT | 453
KASBA, TOWN PANCHAYAT | 316
KATAIYA, TOWN PANCHAYAT | 690
KATIHAR, MUNICIPAL CORPORATION | 664
KATORIA, TOWN PANCHAYAT | 395
KESARIA, TOWN PANCHAYAT | 200
KHAGARIA, MUNICIPALITY | 239
KHAGAUL, MUNICIPALITY | 63
KHIZARSARAI, TOWN PANCHAYAT | 458
KHUSRUPUR, TOWN PANCHAYAT | 224
KISHANGANJ, MUNICIPALITY | 325
KOATH, TOWN PANCHAYAT | 323
KOCHAS, TOWN PANCHAYAT | 61
KOILWAR, TOWN PANCHAYAT | 206
KOPA, TOWN PANCHAYAT | 20
KORHA, TOWN PANCHAYAT | 317
KUDRA, TOWN PANCHAYAT | 228
KURHANI, TOWN PANCHAYAT | 431
KURSELA, TOWN PANCHAYAT | 228
KURTHA, TOWN PANCHAYAT | 42
KUSHESWAR ASTHAN EAST, TOWN PANCHAYAT | 621
LAKHISARAI, MUNICIPALITY | 916
LALGANJ, MUNICIPALITY | 303
LAURIA, TOWN PANCHAYAT | 524
MADHEPURA, MUNICIPALITY | 1254
MADHOPUR SUSTA, TOWN PANCHAYAT | 685
MADHUBANI, MUNICIPAL CORPORATION | 2417
MAHARAJGANJ, TOWN PANCHAYAT | 240
MAHNAR BAZAR, MUNICIPALITY | 60
MAHUA, MUNICIPALITY | 929
MAIRWA, TOWN PANCHAYAT | 201
MAKHDUMPUR, TOWN PANCHAYAT | 938
MANER, TOWN PANCHAYAT | 445
MANIHARI, TOWN PANCHAYAT | 148
MANJHI, TOWN PANCHAYAT | 671
MANSI, TOWN PANCHAYAT | 409
MARHAURA, TOWN PANCHAYAT | 768
MASAURHI, MUNICIPALITY | 523
MASHRAKH, TOWN PANCHAYAT | 494
MINAPUR, TOWN PANCHAYAT | 858
MIRGANJ, MUNICIPALITY | 2081
MIRGANJ, TOWN PANCHAYAT | 512
MOHANIA, TOWN PANCHAYAT | 210
MOKAMEH, MUNICIPALITY | 126
MOTIHARI, MUNICIPAL CORPORATION | 1958
MOTIPUR, MUNICIPALITY | 1051
MUNGER, MUNICIPAL CORPORATION | 301
MURAUL, TOWN PANCHAYAT | 200
MURLIGANJ, TOWN PANCHAYAT | 165
MUSRI GHARARI, TOWN PANCHAYAT | 1569
MUZAFFARPUR, MUNICIPAL CORPORATION | 350
NABINAGAR, TOWN PANCHAYAT | 283
NALANDA, TOWN PANCHAYAT | 572
NARKATIAGANJ, MUNICIPALITY | 82
NARPATGANJ, TOWN PANCHAYAT | 543
NASRIGANJ, TOWN PANCHAYAT | 154
NAUBATPUR, TOWN PANCHAYAT | 515
NAUGACHHIA, MUNICIPALITY | 386
NAUHATTA, TOWN PANCHAYAT | 1401
NAWADA, MUNICIPALITY | 809
NIRMALI, TOWN PANCHAYAT | 236
NOKHA, MUNICIPALITY | 2328
PALIGANJ, TOWN PANCHAYAT | 107
PARBALPUR, TOWN PANCHAYAT | 46
PARBATTA, TOWN PANCHAYAT | 867
PARSA BAZAR, TOWN PANCHAYAT | 1092
PATEPUR, TOWN PANCHAYAT | 693
PATNA MUNICIPAL CORPORATION | 72
PAUAKHALI, TOWN PANCHAYAT | 1345
PAWAPURI, TOWN PANCHAYAT | 648
PHULPARAS, TOWN PANCHAYAT | 1145
PHULWARI SHARIF, MUNICIPALITY | 64
PIPRA, TOWN PANCHAYAT | 647
PIRO, MUNICIPALITY | 325
PIRPAINTI, TOWN PANCHAYAT | 342
PUNPUN, TOWN PANCHAYAT | 352
PURNIA, MUNICIPAL CORPORATION | 1851
RAFIGANJ, TOWN PANCHAYAT | 36
RAHUI, TOWN PANCHAYAT | 399
RAJAULI, TOWN PANCHAYAT | 533
RAJGIR, TOWN PANCHAYAT | 99
RAMGARH, TOWN PANCHAYAT | 170
RAMNAGAR, TOWN PANCHAYAT | 1570
RANIGANJ, TOWN PANCHAYAT | 732
RAXAUL BAZAR, MUNICIPALITY | 423
REVELGANJ, TOWN PANCHAYAT | 277
ROHTAS, TOWN PANCHAYAT | 494
ROSERA, MUNICIPALITY | 889
RUPAULI, TOWN PANCHAYAT | 750
SABOUR, TOWN PANCHAYAT | 234
SAHARSA, MUNICIPAL CORPORATION | 5224
SAHEBGANJ, MUNICIPALITY | 629
SAKRA, TOWN PANCHAYAT | 545
SAMASTIPUR, MUNICIPAL CORPORATION | 1758
SAMPATCHAK, MUNICIPALITY | 124
SANGRAMPUR, TOWN PANCHAYAT | 326
SARAIRANJAN, TOWN PANCHAYAT | 1309
SARAIYA, TOWN PANCHAYAT | 512
SARMERA, TOWN PANCHAYAT | 135
SASARAM, MUNICIPAL CORPORATION | 1722
SHAHPUR PATORI, MUNICIPALITY | 2220
SHAHPUR, TOWN PANCHAYAT | 94
SHEIKHOPUR SARAI, TOWN PANCHAYAT | 245
SHEIKHPURA, MUNICIPALITY | 632
SHEOHAR, TOWN PANCHAYAT | 239
SHERGHATI, MUNICIPALITY | 841
SIKANDRA, TOWN PANCHAYAT | 125
SILAO, TOWN PANCHAYAT | 254
SIMRAHI, TOWN PANCHAYAT | 659
SIMRI BAKHTIYARPUR, TOWN PANCHAYAT | 1902
SINGHESHWAR, TOWN PANCHAYAT | 506
SINGHIA, TOWN PANCHAYAT | 1075
SINGHWARA, TOWN PANCHAYAT | 1094
SITAMARHI, MUNICIPAL CORPORATION | 3691
SIWAN, MUNICIPALITY | 3275
SONBARSA, TOWN PANCHAYAT | 916
SONEPUR, TOWN PANCHAYAT | 100
SOUR BAZAR, TOWN PANCHAYAT | 1626
SUGAULI, TOWN PANCHAYAT | 307
SULTANGANJ, MUNICIPALITY | 167
SUPAUL, MUNICIPALITY | 275
SURSAND, TOWN PANCHAYAT | 1416
SURYAGADHA, MUNICIPALITY | 559
TAJPUR, MUNICIPALITY | 1097
TARAPUR, TOWN PANCHAYAT | 352
TEGHRA, TOWN PANCHAYAT | 458
THAKURGANJ, TOWN PANCHAYAT | 400
TIKARI, MUNICIPALITY | 403
TRIBENIGANJ, MUNICIPALITY | 1621
UDAKISHUNGANJ, MUNICIPALITY | 3794
WARISALIGANJ, TOWN PANCHAYAT | 270
WAZIRGANJ, TOWN PANCHAYAT | 447
YOGAPATTI, TOWN PANCHAYAT | 415

## Grounded
Physical status of Houses under PMAY(U)-2.0
SNo | ULB Name | Houses Sanctioned | Houses at Foundation | Houses at Lintel | Houses at Roof | Houses Completed | Houses Grounded | Houses to be Grounded
1 | Bodh Gaya, Municipality | 4137 | 691 | 1008 | 133 | 0 | 1956 | 2181
2 | Sitamarhi, Municipal Corporation | 3691 | 600 | 916 | 2 | 0 | 1518 | 2173
3 | Madhubani, Municipal Corporation | 2417 | 96 | 497 | 25 | 1 | 619 | 1798
4 | Alamnagar, Town Panchayat | 2023 | 48 | 493 | 4 | 0 | 600 | 1423
5 | Mirganj, Municipality | 2081 | 356 | 532 | 6 | 0 | 899 | 1182
6 | Banmankhi Bazar, Municipality | 1397 | 66 | 156 | 0 | 0 | 228 | 1169
7 | Sursand, Town Panchayat | 1416 | 61 | 210 | 13 | 0 | 307 | 1109
8 | Chakia, Municipality | 1188 | 2 | 133 | 10 | 0 | 146 | 1042
9 | Madhepura, Municipality | 1254 | 148 | 76 | 4 | 0 | 232 | 1022
10 | Bihariganj, Town Panchayat | 1648 | 340 | 290 | 0 | 0 | 652 | 996
11 | Imamganj, Town Panchayat | 1532 | 59 | 551 | 2 | 0 | 616 | 916
12 | Musri Gharari, Town Panchayat | 1569 | 41 | 474 | 138 | 0 | 655 | 914
13 | Ghanshyampur, Town Panchayat | 1443 | 330 | 211 | 0 | 0 | 565 | 878
14 | Nokha, Municipality | 2328 | 778 | 568 | 10 | 0 | 1477 | 851
15 | Bairgania, Municipality | 1449 | 330 | 274 | 1 | 1 | 627 | 822
16 | Bakhri, Municipality | 1845 | 285 | 678 | 9 | 0 | 1054 | 791
17 | Rosera, Municipality | 889 | 86 | 109 | 46 | 1 | 249 | 640
18 | Ghoshi, Town Panchayat | 1441 | 294 | 507 | 20 | 0 | 852 | 589
19 | Dalsinghsarai, Municipality | 1376 | 405 | 323 | 1 | 0 | 797 | 579
20 | Belsand, Town Panchayat | 951 | 131 | 270 | 6 | 1 | 411 | 540
21 | Mahua, Municipality | 929 | 126 | 274 | 81 | 0 | 481 | 448
22 | Sherghati, Municipality | 841 | 190 | 212 | 18 | 0 | 424 | 417
23 | Begusarai, Municipal Corporation | 1507 | 403 | 593 | 67 | 0 | 1113 | 394
24 | Jandaha, Town Panchayat | 1092 | 437 | 171 | 0 | 0 | 702 | 390
25 | Garhani, Town Panchayat | 1186 | 176 | 549 | 93 | 0 | 821 | 365
26 | Purnia, Municipal Corporation | 1851 | 332 | 1041 | 50 | 31 | 1495 | 356
27 | Dighwara, Town Panchayat | 525 | 128 | 44 | 8 | 0 | 199 | 326
28 | Tajpur, Municipality | 1097 | 135 | 506 | 44 | 0 | 781 | 316
29 | Jale, Town Panchayat | 2545 | 213 | 1840 | 103 | 13 | 2230 | 315
30 | Motihari, Municipal Corporation | 1958 | 970 | 399 | 18 | 0 | 1664 | 294
31 | Jagdishpur, Town Panchayat | 521 | 35 | 149 | 19 | 1 | 233 | 288
32 | Jankinagar, Town Panchayat | 1360 | 654 | 272 | 0 | 0 | 1072 | 288
33 | Tribeniganj, Municipality | 1621 | 463 | 798 | 7 | 0 | 1335 | 286
34 | Goraul, Town Panchayat | 812 | 37 | 473 | 17 | 1 | 541 | 271
35 | Bharwara, Town Panchayat | 792 | 68 | 408 | 47 | 0 | 535 | 257
36 | Lakhisarai, Municipality | 916 | 172 | 438 | 38 | 0 | 663 | 253
37 | Barun, Town Panchayat | 604 | 119 | 223 | 14 | 0 | 356 | 248
38 | Gaya, Municipal Corporation | 1471 | 68 | 1129 | 17 | 11 | 1227 | 244
39 | Hajipur, Municipality | 1708 | 583 | 746 | 12 | 5 | 1480 | 228
40 | Kishanganj, Municipality | 325 | 41 | 57 | 4 | 0 | 102 | 223
41 | Simrahi, Town Panchayat | 659 | 343 | 62 | 10 | 0 | 442 | 217
42 | Ramnagar, Town Panchayat | 1570 | 415 | 735 | 25 | 0 | 1354 | 216
43 | Kasba, Town Panchayat | 316 | 32 | 59 | 7 | 0 | 102 | 214
44 | Dobhi, Town Panchayat | 649 | 396 | 36 | 0 | 0 | 436 | 213
45 | Maner, Town Panchayat | 445 | 104 | 111 | 15 | 0 | 233 | 212
46 | Pauakhali, Town Panchayat | 1345 | 843 | 267 | 15 | 0 | 1142 | 203
47 | Kusheswar Asthan East, Town Panchayat | 621 | 214 | 93 | 62 | 0 | 420 | 201
48 | Bihat, Municipality | 1933 | 335 | 851 | 124 | 2 | 1733 | 200
49 | Nauhatta, Town Panchayat | 1401 | 663 | 478 | 0 | 0 | 1203 | 198
50 | Balia, Municipality | 268 | 27 | 48 | 0 | 0 | 75 | 193
51 | Sarairanjan, Town Panchayat | 1309 | 274 | 598 | 192 | 1 | 1117 | 192
52 | Dhamdaha, Town Panchayat | 664 | 112 | 345 | 4 | 0 | 473 | 191
53 | Sahebganj, Municipality | 629 | 155 | 262 | 14 | 0 | 440 | 189
54 | Naugachhia, Municipality | 386 | 41 | 111 | 22 | 2 | 199 | 187
55 | Bettiah, Municipal Corporation | 508 | 147 | 151 | 21 | 0 | 321 | 187
56 | Shahpur Patori, Municipality | 2220 | 534 | 1298 | 5 | 0 | 2033 | 187
57 | Singhwara, Town Panchayat | 1094 | 222 | 678 | 12 | 0 | 913 | 181
58 | Daudnagar, Municipality | 1309 | 47 | 1076 | 6 | 0 | 1132 | 177
59 | Amarpur, Town Panchayat | 468 | 174 | 100 | 12 | 0 | 291 | 177
60 | Biraul, Town Panchayat | 838 | 528 | 17 | 8 | 0 | 662 | 176
61 | Pawapuri, Town Panchayat | 648 | 80 | 321 | 63 | 0 | 472 | 176
62 | Makhdumpur, Town Panchayat | 938 | 360 | 364 | 33 | 4 | 763 | 175
63 | Singhia, Town Panchayat | 1075 | 63 | 822 | 11 | 0 | 901 | 174
64 | Phulparas, Town Panchayat | 1145 | 170 | 717 | 26 | 0 | 975 | 170
65 | Rupauli, Town Panchayat | 750 | 244 | 321 | 2 | 0 | 581 | 169
66 | Simri Bakhtiyarpur, Town Panchayat | 1902 | 722 | 962 | 41 | 0 | 1735 | 167
67 | Dehri Dalmianagar, Municipality | 619 | 119 | 314 | 23 | 0 | 458 | 161
68 | Rohtas, Town Panchayat | 494 | 146 | 176 | 11 | 0 | 333 | 161
69 | Pipra, Town Panchayat | 647 | 187 | 268 | 0 | 0 | 487 | 160
70 | Jhajha, Municipality | 876 | 41 | 649 | 30 | 2 | 723 | 153
71 | Kurhani, Town Panchayat | 431 | 100 | 156 | 0 | 0 | 278 | 153
72 | Manjhi, Town Panchayat | 671 | 365 | 48 | 1 | 2 | 519 | 152
73 | Benipur, Municipality | 802 | 292 | 225 | 5 | 0 | 651 | 151
74 | Fatehpur, Town Panchayat | 650 | 52 | 330 | 53 | 0 | 501 | 149
75 | Nabinagar, Town Panchayat | 283 | 74 | 63 | 2 | 0 | 139 | 144
76 | Darbhanga, Municipal Corporation | 950 | 343 | 387 | 69 | 6 | 806 | 144
77 | Habibpur, Town Panchayat | 745 | 89 | 371 | 139 | 0 | 602 | 143
78 | Chapra, Municipal Corporation | 807 | 195 | 404 | 7 | 0 | 667 | 140
79 | Ekma Bazar, Town Panchayat | 561 | 155 | 221 | 37 | 0 | 421 | 140
80 | Raniganj, Town Panchayat | 732 | 359 | 114 | 0 | 0 | 593 | 139
81 | Piro, Municipality | 325 | 63 | 94 | 28 | 0 | 187 | 138
82 | Bagaha, Municipality | 815 | 69 | 516 | 10 | 80 | 677 | 138
83 | Udakishunganj, Municipality | 3794 | 1596 | 1867 | 24 | 0 | 3658 | 136
84 | Minapur, Town Panchayat | 858 | 154 | 545 | 19 | 1 | 725 | 133
85 | Lauria, Town Panchayat | 524 | 192 | 162 | 13 | 0 | 393 | 131
86 | Nawada, Municipality | 809 | 191 | 344 | 139 | 5 | 681 | 128
87 | Sakra, Town Panchayat | 545 | 127 | 235 | 43 | 3 | 420 | 125
88 | Asthawan, Town Panchayat | 865 | 65 | 663 | 12 | 0 | 741 | 124
89 | Maharajganj, Town Panchayat | 240 | 20 | 84 | 0 | 0 | 117 | 123
90 | Sheikhpura, Municipality | 632 | 199 | 273 | 29 | 0 | 510 | 122
91 | Kamtaul Ahiyari, Town Panchayat | 875 | 158 | 344 | 4 | 0 | 755 | 120
92 | Guthani, Town Panchayat | 430 | 40 | 268 | 0 | 0 | 311 | 119
93 | Sasaram, Municipal Corporation | 1722 | 505 | 1056 | 12 | 0 | 1604 | 118
94 | Kataiya, Town Panchayat | 690 | 71 | 441 | 11 | 7 | 574 | 116
95 | Khusrupur, Town Panchayat | 224 | 12 | 87 | 9 | 0 | 108 | 116
96 | Muzaffarpur, Municipal Corporation | 350 | 56 | 147 | 30 | 0 | 235 | 115
97 | Saharsa, Municipal Corporation | 5224 | 1339 | 3701 | 3 | 57 | 5109 | 115
98 | Itarhi, Town Panchayat | 409 | 133 | 142 | 5 | 0 | 295 | 114
99 | Giriak, Town Panchayat | 333 | 164 | 35 | 2 | 0 | 220 | 113
100 | Motipur, Municipality | 1051 | 214 | 594 | 33 | 25 | 940 | 111
101 | Sour Bazar, Town Panchayat | 1626 | 6 | 944 | 4 | 0 | 1517 | 109
102 | Birpur, Town Panchayat | 213 | 34 | 65 | 4 | 0 | 104 | 109
103 | Arwal, Municipality | 229 | 34 | 59 | 25 | 3 | 121 | 108
104 | Parbatta, Town Panchayat | 867 | 36 | 721 | 2 | 0 | 759 | 108
105 | Amour, Town Panchayat | 815 | 258 | 408 | 32 | 0 | 708 | 107
106 | Bhawanipur, Town Panchayat | 347 | 90 | 148 | 0 | 0 | 240 | 107
107 | Hayaghat, Town Panchayat | 400 | 76 | 164 | 11 | 0 | 294 | 106
108 | Siwan, Municipality | 3275 | 1611 | 1372 | 124 | 0 | 3169 | 106
109 | Sonbarsa, Town Panchayat | 916 | 137 | 624 | 26 | 0 | 811 | 105
110 | Jainagar, Town Panchayat | 358 | 55 | 134 | 35 | 0 | 256 | 102
111 | Mokameh, Municipality | 126 | 9 | 11 | 3 | 0 | 24 | 102
112 | Araria, Municipality | 207 | 79 | 26 | 1 | 0 | 106 | 101
113 | Benipatti, Town Panchayat | 541 | 10 | 390 | 39 | 0 | 440 | 101
114 | Saraiya, Town Panchayat | 512 | 23 | 384 | 4 | 0 | 412 | 100
115 | Madhopur Susta, Town Panchayat | 685 | 250 | 276 | 5 | 0 | 589 | 96
116 | Mansi, Town Panchayat | 409 | 69 | 227 | 20 | 0 | 317 | 92
117 | Harnaut, Town Panchayat | 260 | 25 | 140 | 0 | 0 | 168 | 92
118 | Lalganj, Municipality | 303 | 66 | 111 | 34 | 0 | 214 | 89
119 | Wazirganj, Town Panchayat | 447 | 313 | 8 | 0 | 0 | 361 | 86
120 | Gogri Jamalpur, Municipality | 1128 | 231 | 737 | 24 | 7 | 1042 | 86
121 | Thakurganj, Town Panchayat | 400 | 125 | 131 | 39 | 1 | 314 | 86
122 | Barauni, Municipality | 557 | 2 | 457 | 0 | 0 | 472 | 85
123 | Jhanjharpur, Municipality | 639 | 74 | 357 | 19 | 11 | 554 | 85
124 | Alauli, Town Panchayat | 611 | 121 | 404 | 0 | 0 | 527 | 84
125 | Biharsharif, Municipal Corporation | 720 | 249 | 387 | 1 | 0 | 637 | 83
126 | Mashrakh, Town Panchayat | 494 | 90 | 308 | 12 | 0 | 411 | 83
127 | Chewara, Town Panchayat | 181 | 13 | 85 | 0 | 0 | 98 | 83
128 | Kanti, Municipality | 339 | 65 | 179 | 9 | 0 | 258 | 81
129 | Jehanabad, Municipality | 338 | 64 | 175 | 17 | 1 | 258 | 80
130 | Nirmali, Town Panchayat | 236 | 79 | 74 | 1 | 0 | 156 | 80
131 | Revelganj, Town Panchayat | 277 | 60 | 101 | 23 | 0 | 198 | 79
132 | Fatwah, Municipality | 524 | 129 | 281 | 18 | 0 | 446 | 78
133 | Masaurhi, Municipality | 523 | 173 | 255 | 13 | 0 | 446 | 77
134 | Parsa Bazar, Town Panchayat | 1092 | 385 | 525 | 35 | 1 | 1015 | 77
135 | Supaul, Municipality | 275 | 53 | 132 | 11 | 0 | 198 | 77
136 | Warisaliganj, Town Panchayat | 270 | 59 | 66 | 63 | 1 | 195 | 75
137 | Mirganj, Town Panchayat | 512 | 159 | 260 | 11 | 0 | 437 | 75
138 | Jogabani, Municipality | 659 | 108 | 437 | 31 | 2 | 586 | 73
139 | Rajauli, Town Panchayat | 533 | 140 | 283 | 21 | 0 | 460 | 73
140 | Karakat, Town Panchayat | 453 | 68 | 301 | 0 | 0 | 381 | 72
141 | Champanagar, Town Panchayat | 529 | 104 | 353 | 0 | 0 | 458 | 71
142 | Akbarnagar, Town Panchayat | 420 | 63 | 230 | 51 | 0 | 350 | 70
143 | Silao, Town Panchayat | 254 | 22 | 113 | 39 | 9 | 184 | 70
144 | Patepur, Town Panchayat | 693 | 265 | 325 | 24 | 1 | 624 | 69
145 | Bounsi, Town Panchayat | 596 | 40 | 439 | 48 | 0 | 529 | 67
146 | Barbigha, Municipality | 436 | 52 | 282 | 32 | 0 | 370 | 66
147 | Barari, Town Panchayat | 297 | 152 | 77 | 2 | 0 | 232 | 65
148 | Sabour, Town Panchayat | 234 | 38 | 121 | 13 | 0 | 172 | 62
149 | Baruraaj, Town Panchayat | 814 | 272 | 359 | 15 | 2 | 752 | 62
150 | Bakhtiyarpur, Municipality | 179 | 88 | 28 | 1 | 0 | 117 | 62
151 | Hasanpura, Town Panchayat | 261 | 64 | 136 | 0 | 0 | 200 | 61
152 | Teghra, Town Panchayat | 458 | 94 | 273 | 20 | 0 | 398 | 60
153 | Kochas, Town Panchayat | 61 | 2 | 0 | 0 | 0 | 2 | 59
154 | Pirpainti, Town Panchayat | 342 | 50 | 219 | 15 | 0 | 284 | 58
155 | Marhaura, Town Panchayat | 768 | 196 | 323 | 9 | 0 | 710 | 58
156 | Kahalgaon, Town Panchayat | 245 | 16 | 96 | 74 | 0 | 188 | 57
157 | Areraj, Town Panchayat | 329 | 118 | 116 | 37 | 0 | 272 | 57
158 | Sheikhopur Sarai, Town Panchayat | 245 | 102 | 80 | 8 | 0 | 191 | 54
159 | Narpatganj, Town Panchayat | 543 | 175 | 309 | 1 | 0 | 490 | 53
160 | Nalanda, Town Panchayat | 572 | 88 | 405 | 19 | 0 | 519 | 53
161 | Suryagadha, Municipality | 559 | 45 | 437 | 20 | 0 | 507 | 52
162 | Singheshwar, Town Panchayat | 506 | 135 | 319 | 0 | 0 | 455 | 51
163 | Janakpur Road, Municipality | 2256 | 505 | 1057 | 549 | 83 | 2205 | 51
164 | Bikram, Town Panchayat | 179 | 39 | 76 | 11 | 3 | 129 | 50
165 | Punpun, Town Panchayat | 352 | 137 | 147 | 0 | 0 | 303 | 49
166 | Kako, Town Panchayat | 233 | 93 | 88 | 0 | 0 | 185 | 48
167 | Bhabua, Municipality | 346 | 116 | 162 | 14 | 0 | 299 | 47
168 | Haweli Kharagpur, Municipality | 320 | 64 | 192 | 10 | 0 | 274 | 46
169 | Buxar, Municipality | 348 | 73 | 206 | 13 | 0 | 305 | 43
170 | Sangrampur, Town Panchayat | 326 | 103 | 157 | 5 | 0 | 285 | 41
171 | Sugauli, Town Panchayat | 307 | 86 | 160 | 1 | 10 | 268 | 39
172 | Mairwa, Town Panchayat | 201 | 39 | 77 | 2 | 0 | 162 | 39
173 | Koilwar, Town Panchayat | 206 | 27 | 120 | 19 | 0 | 168 | 38
174 | Hata, Town Panchayat | 504 | 167 | 280 | 2 | 0 | 466 | 38
175 | Korha, Town Panchayat | 317 | 75 | 195 | 0 | 0 | 279 | 38
176 | Murliganj, Town Panchayat | 165 | 31 | 92 | 5 | 0 | 128 | 37
177 | Manihari, Town Panchayat | 148 | 76 | 36 | 0 | 0 | 112 | 36
178 | Mohania, Town Panchayat | 210 | 21 | 136 | 14 | 1 | 175 | 35
179 | Khagaria, Municipality | 239 | 71 | 130 | 2 | 0 | 204 | 35
180 | Andar, Town Panchayat | 107 | 19 | 53 | 0 | 0 | 72 | 35
181 | Bihta, Municipality | 816 | 523 | 250 | 2 | 0 | 782 | 34
182 | Sarmera, Town Panchayat | 135 | 5 | 80 | 15 | 0 | 102 | 33
183 | Jamui, Municipality | 141 | 48 | 57 | 1 | 2 | 109 | 32
184 | Barahiya, Municipality | 197 | 44 | 93 | 27 | 0 | 165 | 32
185 | Samastipur, Municipal Corporation | 1758 | 258 | 1138 | 34 | 4 | 1726 | 32
186 | Bhagalpur, Municipal Corporation | 547 | 138 | 359 | 16 | 0 | 516 | 31
187 | Dumraon, Municipality | 372 | 39 | 280 | 17 | 4 | 341 | 31
188 | Sheohar, Town Panchayat | 239 | 30 | 178 | 0 | 0 | 208 | 31
189 | Bahadurganj, Town Panchayat | 363 | 76 | 232 | 8 | 0 | 333 | 30
190 | Koath, Town Panchayat | 323 | 63 | 129 | 78 | 21 | 294 | 29
191 | Nasriganj, Town Panchayat | 154 | 78 | 38 | 0 | 0 | 125 | 29
192 | Rahui, Town Panchayat | 399 | 78 | 293 | 0 | 0 | 371 | 28
193 | Chausa, Town Panchayat | 212 | 65 | 118 | 1 | 0 | 185 | 27
194 | Dinara, Town Panchayat | 203 | 27 | 144 | 2 | 0 | 177 | 26
195 | Barauli, Municipality | 202 | 132 | 28 | 5 | 0 | 177 | 25
196 | Ramgarh, Town Panchayat | 170 | 4 | 138 | 3 | 0 | 145 | 25
197 | Deo, Town Panchayat | 161 | 20 | 116 | 2 | 0 | 138 | 23
198 | Hathua, Town Panchayat | 168 | 101 | 33 | 0 | 0 | 145 | 23
199 | Khizarsarai, Town Panchayat | 458 | 126 | 295 | 12 | 1 | 436 | 22
200 | Yogapatti, Town Panchayat | 415 | 19 | 354 | 17 | 0 | 393 | 22
201 | Chenari, Town Panchayat | 376 | 15 | 322 | 14 | 0 | 354 | 22
202 | Behea, Town Panchayat | 230 | 22 | 169 | 10 | 8 | 210 | 20
203 | Tikari, Municipality | 403 | 68 | 312 | 3 | 0 | 384 | 19
204 | Kudra, Town Panchayat | 228 | 16 | 184 | 7 | 0 | 209 | 19
205 | Muraul, Town Panchayat | 200 | 23 | 145 | 13 | 0 | 181 | 19
206 | Naubatpur, Town Panchayat | 515 | 178 | 288 | 23 | 0 | 496 | 19
207 | Paliganj, Town Panchayat | 107 | 20 | 65 | 2 | 0 | 88 | 19
208 | Kesaria, Town Panchayat | 200 | 58 | 96 | 24 | 0 | 181 | 19
209 | Baisi, Town Panchayat | 717 | 65 | 398 | 233 | 0 | 698 | 19
210 | Barsoi, Town Panchayat | 74 | 34 | 14 | 4 | 1 | 56 | 18
211 | Kursela, Town Panchayat | 228 | 81 | 110 | 21 | 0 | 212 | 16
212 | Chanpatia, Town Panchayat | 170 | 54 | 81 | 14 | 0 | 154 | 16
213 | Sultanganj, Municipality | 167 | 30 | 95 | 21 | 0 | 153 | 14
214 | Katihar, Municipal Corporation | 664 | 229 | 370 | 51 | 0 | 650 | 14
215 | Tarapur, Town Panchayat | 352 | 32 | 262 | 43 | 0 | 338 | 14
216 | Gopalpur, Town Panchayat | 262 | 215 | 7 | 0 | 0 | 248 | 14
217 | Sikandra, Town Panchayat | 125 | 9 | 102 | 1 | 0 | 112 | 13
218 | Sonepur, Town Panchayat | 100 | 17 | 60 | 8 | 1 | 87 | 13
219 | Barharia, Town Panchayat | 294 | 27 | 220 | 10 | 0 | 281 | 13
220 | Baheri, Town Panchayat | 316 | 75 | 189 | 0 | 0 | 304 | 12
221 | Asarganj, Town Panchayat | 161 | 15 | 111 | 23 | 0 | 149 | 12
222 | Narkatiaganj, Municipality | 82 | 27 | 40 | 2 | 0 | 70 | 12
223 | Jokihat, Town Panchayat | 249 | 12 | 212 | 1 | 1 | 239 | 10
224 | Gopalganj, Municipality | 212 | 141 | 56 | 2 | 0 | 202 | 10
225 | Amdabad, Town Panchayat | 377 | 59 | 308 | 0 | 0 | 367 | 10
226 | Beldaur, Town Panchayat | 320 | 12 | 296 | 1 | 0 | 310 | 10
227 | Rajgir, Town Panchayat | 99 | 4 | 56 | 29 | 0 | 89 | 10
228 | Brahmpur, Town Panchayat | 246 | 8 | 218 | 11 | 0 | 237 | 9
229 | Munger, Municipal Corporation | 301 | 64 | 197 | 12 | 16 | 292 | 9
230 | Basantpur, Town Panchayat | 187 | 106 | 69 | 0 | 0 | 178 | 9
231 | Aurangabad, Municipality | 221 | 20 | 141 | 51 | 0 | 213 | 8
232 | Arrah, Municipal Corporation | 161 | 24 | 123 | 5 | 1 | 153 | 8
233 | Bikramganj, Municipality | 120 | 22 | 63 | 25 | 0 | 112 | 8
234 | Hisua, Town Panchayat | 750 | 690 | 43 | 9 | 0 | 743 | 7
235 | Forbesganj, Municipality | 109 | 21 | 73 | 8 | 1 | 104 | 5
236 | Katoria, Town Panchayat | 395 | 33 | 355 | 1 | 0 | 391 | 4
237 | Shahpur, Town Panchayat | 94 | 17 | 51 | 16 | 5 | 90 | 4
238 | Parbalpur, Town Panchayat | 46 | 9 | 33 | 0 | 0 | 42 | 4
239 | Khagaul, Municipality | 63 | 18 | 23 | 15 | 0 | 59 | 4
240 | Kopa, Town Panchayat | 20 | 10 | 6 | 0 | 0 | 16 | 4
241 | Banka, Municipality | 312 | 120 | 164 | 25 | 0 | 309 | 3
242 | Barh, Municipality | 118 | 27 | 62 | 16 | 0 | 115 | 3
243 | Phulwari Sharif, Municipality | 64 | 20 | 37 | 3 | 1 | 61 | 3
244 | Islampur, Municipality | 56 | 8 | 37 | 9 | 0 | 54 | 2
245 | Dinapur Nizamat, Municipality | 131 | 22 | 83 | 21 | 0 | 129 | 2
246 | Sampatchak, Municipality | 124 | 24 | 47 | 49 | 0 | 122 | 2
247 | Balrampur, Town Panchayat | 108 | 42 | 53 | 8 | 0 | 107 | 1
248 | Ekangarsarai, Town Panchayat | 35 | 23 | 10 | 1 | 0 | 34 | 1
249 | Dhaka, Municipality | 135 | 223 | 72 | 9 | 8 | 135 | 0
250 | Ghoghardiha, Town Panchayat | 160 | 85 | 52 | 7 | 0 | 160 | 0
251 | Bangaon, Town Panchayat | 1310 | 339 | 917 | 2 | 0 | 1310 | 0
252 | Hilsa, Municipality | 218 | 42 | 154 | 21 | 3 | 218 | 0
253 | Raxaul Bazar, Municipality | 423 | 200 | 152 | 43 | 0 | 423 | 0
254 | Jamalpur, Municipality | 161 | 35 | 71 | 46 | 9 | 161 | 0
255 | Kurtha, Town Panchayat | 42 | 12 | 28 | 2 | 0 | 42 | 0
256 | Rafiganj, Town Panchayat | 36 | 2 | 23 | 10 | 1 | 36 | 0
257 | Chandi, Town Panchayat | 85 | 39 | 46 | 0 | 0 | 85 | 0
258 | Patna Municipal Corporation | 72 | 10 | 40 | 22 | 0 | 72 | 0
259 | Mahnar Bazar, Municipality | 60 | 11 | 43 | 2 | 1 | 60 | 0
| Total | 175235 | 40916 | 77763 | 5661 | 488 | 131175 | 44060

## lintel
Physical status of Houses at Lintel Level under PMAY(U)-2.0
SNo | ULB Name | Houses Sanctioned | Houses Grounded | Houses at Lintel | Houses at Foundation | Houses at Lintel | Houses at Roof | Houses Completed | Houses to be Lintel
1 | Udakishunganj, Municipality | 3794 | 3658 | 1891 | 1596 | 1867 | 24 | 0 | 1767
2 | Siwan, Municipality | 3275 | 3169 | 1496 | 1611 | 1372 | 124 | 0 | 1673
3 | Saharsa, Municipal Corporation | 5224 | 5109 | 3761 | 1339 | 3701 | 3 | 57 | 1348
4 | Motihari, Municipal Corporation | 1958 | 1664 | 417 | 970 | 399 | 18 | 0 | 1247
5 | Nokha, Municipality | 2328 | 1477 | 578 | 778 | 568 | 10 | 0 | 899
6 | Pauakhali, Town Panchayat | 1345 | 1142 | 282 | 843 | 267 | 15 | 0 | 860
7 | Bodh Gaya, Municipality | 4137 | 1956 | 1141 | 691 | 1008 | 133 | 0 | 815
8 | Jankinagar, Town Panchayat | 1360 | 1072 | 272 | 654 | 272 | 0 | 0 | 800
9 | Bihat, Municipality | 1933 | 1733 | 977 | 335 | 851 | 124 | 2 | 756
10 | Simri Bakhtiyarpur, Town Panchayat | 1902 | 1735 | 1003 | 722 | 962 | 41 | 0 | 732
11 | Shahpur Patori, Municipality | 2220 | 2033 | 1303 | 534 | 1298 | 5 | 0 | 730
12 | Nauhatta, Town Panchayat | 1401 | 1203 | 478 | 663 | 478 | 0 | 0 | 725
13 | Hajipur, Municipality | 1708 | 1480 | 763 | 583 | 746 | 12 | 5 | 717
14 | Hisua, Town Panchayat | 750 | 743 | 52 | 690 | 43 | 9 | 0 | 691
15 | Biraul, Town Panchayat | 838 | 662 | 25 | 528 | 17 | 8 | 0 | 637
16 | Sitamarhi, Municipal Corporation | 3691 | 1518 | 918 | 600 | 916 | 2 | 0 | 600
17 | Ramnagar, Town Panchayat | 1570 | 1354 | 760 | 415 | 735 | 25 | 0 | 594
18 | Sour Bazar, Town Panchayat | 1626 | 1517 | 948 | 6 | 944 | 4 | 0 | 569
19 | Samastipur, Municipal Corporation | 1758 | 1726 | 1176 | 258 | 1138 | 34 | 4 | 550
20 | Sasaram, Municipal Corporation | 1722 | 1604 | 1068 | 505 | 1056 | 12 | 0 | 536
21 | Jandaha, Town Panchayat | 1092 | 702 | 171 | 437 | 171 | 0 | 0 | 531
22 | Tribeniganj, Municipality | 1621 | 1335 | 805 | 463 | 798 | 7 | 0 | 530
23 | Bihta, Municipality | 816 | 782 | 252 | 523 | 250 | 2 | 0 | 530
24 | Janakpur Road, Municipality | 2256 | 2205 | 1689 | 505 | 1057 | 549 | 83 | 516
25 | Raniganj, Town Panchayat | 732 | 593 | 114 | 359 | 114 | 0 | 0 | 479
26 | Dalsinghsarai, Municipality | 1376 | 797 | 324 | 405 | 323 | 1 | 0 | 473
27 | Manjhi, Town Panchayat | 671 | 519 | 51 | 365 | 48 | 1 | 2 | 468
28 | Parsa Bazar, Town Panchayat | 1092 | 1015 | 561 | 385 | 525 | 35 | 1 | 454
29 | Begusarai, Municipal Corporation | 1507 | 1113 | 660 | 403 | 593 | 67 | 0 | 453
30 | Benipur, Municipality | 802 | 651 | 230 | 292 | 225 | 5 | 0 | 421
31 | Kamtaul Ahiyari, Town Panchayat | 875 | 755 | 348 | 158 | 344 | 4 | 0 | 407
32 | Dobhi, Town Panchayat | 649 | 436 | 36 | 396 | 36 | 0 | 0 | 400
33 | Bangaon, Town Panchayat | 1310 | 1310 | 919 | 339 | 917 | 2 | 0 | 391
34 | Marhaura, Town Panchayat | 768 | 710 | 332 | 196 | 323 | 9 | 0 | 378
35 | Baruraaj, Town Panchayat | 814 | 752 | 376 | 272 | 359 | 15 | 2 | 376
36 | Purnia, Municipal Corporation | 1851 | 1495 | 1122 | 332 | 1041 | 50 | 31 | 373
37 | Simrahi, Town Panchayat | 659 | 442 | 72 | 343 | 62 | 10 | 0 | 370
38 | Bakhri, Municipality | 1845 | 1054 | 687 | 285 | 678 | 9 | 0 | 367
39 | Bihariganj, Town Panchayat | 1648 | 652 | 290 | 340 | 290 | 0 | 0 | 362
40 | Makhdumpur, Town Panchayat | 938 | 763 | 401 | 360 | 364 | 33 | 4 | 362
41 | Mirganj, Municipality | 2081 | 899 | 538 | 356 | 532 | 6 | 0 | 361
42 | Ghanshyampur, Town Panchayat | 1443 | 565 | 211 | 330 | 211 | 0 | 0 | 354
43 | Wazirganj, Town Panchayat | 447 | 361 | 8 | 313 | 8 | 0 | 0 | 353
44 | Bairgania, Municipality | 1449 | 627 | 276 | 330 | 274 | 1 | 1 | 351
45 | Darbhanga, Municipal Corporation | 950 | 806 | 462 | 343 | 387 | 69 | 6 | 344
46 | Sarairanjan, Town Panchayat | 1309 | 1117 | 791 | 274 | 598 | 192 | 1 | 326
47 | Ghoshi, Town Panchayat | 1441 | 852 | 527 | 294 | 507 | 20 | 0 | 325
48 | Madhopur Susta, Town Panchayat | 685 | 589 | 281 | 250 | 276 | 5 | 0 | 308
49 | Motipur, Municipality | 1051 | 940 | 652 | 214 | 594 | 33 | 25 | 288
50 | Jale, Town Panchayat | 2545 | 2230 | 1956 | 213 | 1840 | 103 | 13 | 274
51 | Gogri Jamalpur, Municipality | 1128 | 1042 | 768 | 231 | 737 | 24 | 7 | 274
52 | Patepur, Town Panchayat | 693 | 624 | 350 | 265 | 325 | 24 | 1 | 274
53 | Amour, Town Panchayat | 815 | 708 | 440 | 258 | 408 | 32 | 0 | 268
54 | Kusheswar Asthan East, Town Panchayat | 621 | 420 | 155 | 214 | 93 | 62 | 0 | 265
55 | Rupauli, Town Panchayat | 750 | 581 | 323 | 244 | 321 | 2 | 0 | 258
56 | Chapra, Municipal Corporation | 807 | 667 | 411 | 195 | 404 | 7 | 0 | 256
57 | Biharsharif, Municipal Corporation | 720 | 637 | 388 | 249 | 387 | 1 | 0 | 249
58 | Gopalpur, Town Panchayat | 262 | 248 | 7 | 215 | 7 | 0 | 0 | 241
59 | Phulparas, Town Panchayat | 1145 | 975 | 743 | 170 | 717 | 26 | 0 | 232
60 | Tajpur, Municipality | 1097 | 781 | 550 | 135 | 506 | 44 | 0 | 231
61 | Katihar, Municipal Corporation | 664 | 650 | 421 | 229 | 370 | 51 | 0 | 229
62 | Raxaul Bazar, Municipality | 423 | 423 | 195 | 200 | 152 | 43 | 0 | 228
63 | Singhwara, Town Panchayat | 1094 | 913 | 690 | 222 | 678 | 12 | 0 | 223
64 | Pipra, Town Panchayat | 647 | 487 | 268 | 187 | 268 | 0 | 0 | 219
65 | Lauria, Town Panchayat | 524 | 393 | 175 | 192 | 162 | 13 | 0 | 218
66 | Sheikhpura, Municipality | 632 | 510 | 302 | 199 | 273 | 29 | 0 | 208
67 | Sherghati, Municipality | 841 | 424 | 230 | 190 | 212 | 18 | 0 | 194
68 | Nawada, Municipality | 809 | 681 | 488 | 191 | 344 | 139 | 5 | 193
69 | Lakhisarai, Municipality | 916 | 663 | 476 | 172 | 438 | 38 | 0 | 187
70 | Naubatpur, Town Panchayat | 515 | 496 | 311 | 178 | 288 | 23 | 0 | 185
71 | Hata, Town Panchayat | 504 | 466 | 282 | 167 | 280 | 2 | 0 | 184
72 | Giriak, Town Panchayat | 333 | 220 | 37 | 164 | 35 | 2 | 0 | 183
73 | Narpatganj, Town Panchayat | 543 | 490 | 310 | 175 | 309 | 1 | 0 | 180
74 | Garhani, Town Panchayat | 1186 | 821 | 642 | 176 | 549 | 93 | 0 | 179
75 | Amarpur, Town Panchayat | 468 | 291 | 112 | 174 | 100 | 12 | 0 | 179
76 | Masaurhi, Municipality | 523 | 446 | 268 | 173 | 255 | 13 | 0 | 178
77 | Jhanjharpur, Municipality | 639 | 554 | 387 | 74 | 357 | 19 | 11 | 167
78 | Mirganj, Town Panchayat | 512 | 437 | 271 | 159 | 260 | 11 | 0 | 166
79 | Sahebganj, Municipality | 629 | 440 | 276 | 155 | 262 | 14 | 0 | 164
80 | Ekma Bazar, Town Panchayat | 561 | 421 | 258 | 155 | 221 | 37 | 0 | 163
81 | Sonbarsa, Town Panchayat | 916 | 811 | 650 | 137 | 624 | 26 | 0 | 161
82 | Minapur, Town Panchayat | 858 | 725 | 565 | 154 | 545 | 19 | 1 | 160
83 | Rajauli, Town Panchayat | 533 | 460 | 304 | 140 | 283 | 21 | 0 | 156
84 | Punpun, Town Panchayat | 352 | 303 | 147 | 137 | 147 | 0 | 0 | 156
85 | Barari, Town Panchayat | 297 | 232 | 79 | 152 | 77 | 2 | 0 | 153
86 | Madhepura, Municipality | 1254 | 232 | 80 | 148 | 76 | 4 | 0 | 152
87 | Bettiah, Municipal Corporation | 508 | 321 | 172 | 147 | 151 | 21 | 0 | 149
88 | Itarhi, Town Panchayat | 409 | 295 | 147 | 133 | 142 | 5 | 0 | 148
89 | Dighwara, Town Panchayat | 525 | 199 | 52 | 128 | 44 | 8 | 0 | 147
90 | Fatwah, Municipality | 524 | 446 | 299 | 129 | 281 | 18 | 0 | 147
91 | Rohtas, Town Panchayat | 494 | 333 | 187 | 146 | 176 | 11 | 0 | 146
92 | Barauli, Municipality | 202 | 177 | 33 | 132 | 28 | 5 | 0 | 144
93 | Gopalganj, Municipality | 212 | 202 | 58 | 141 | 56 | 2 | 0 | 144
94 | Thakurganj, Town Panchayat | 400 | 314 | 171 | 125 | 131 | 39 | 1 | 143
95 | Bhagalpur, Municipal Corporation | 547 | 516 | 375 | 138 | 359 | 16 | 0 | 141
96 | Sakra, Town Panchayat | 545 | 420 | 281 | 127 | 235 | 43 | 3 | 139
97 | Singheshwar, Town Panchayat | 506 | 455 | 319 | 135 | 319 | 0 | 0 | 136
98 | Belsand, Town Panchayat | 951 | 411 | 277 | 131 | 270 | 6 | 1 | 134
99 | Khizarsarai, Town Panchayat | 458 | 436 | 308 | 126 | 295 | 12 | 1 | 128
100 | Mahua, Municipality | 929 | 481 | 355 | 126 | 274 | 81 | 0 | 126
101 | Dhamdaha, Town Panchayat | 664 | 473 | 349 | 112 | 345 | 4 | 0 | 124
102 | Alauli, Town Panchayat | 611 | 527 | 404 | 121 | 404 | 0 | 0 | 123
103 | Bhabua, Municipality | 346 | 299 | 176 | 116 | 162 | 14 | 0 | 123
104 | Sangrampur, Town Panchayat | 326 | 285 | 162 | 103 | 157 | 5 | 0 | 123
105 | Kurhani, Town Panchayat | 431 | 278 | 156 | 100 | 156 | 0 | 0 | 122
106 | Dehri Dalmianagar, Municipality | 619 | 458 | 337 | 119 | 314 | 23 | 0 | 121
107 | Banka, Municipality | 312 | 309 | 189 | 120 | 164 | 25 | 0 | 120
108 | Barun, Town Panchayat | 604 | 356 | 237 | 119 | 223 | 14 | 0 | 119
109 | Hayaghat, Town Panchayat | 400 | 294 | 175 | 76 | 164 | 11 | 0 | 119
110 | Areraj, Town Panchayat | 329 | 272 | 153 | 118 | 116 | 37 | 0 | 119
111 | Fatehpur, Town Panchayat | 650 | 501 | 383 | 52 | 330 | 53 | 0 | 118
112 | Jogabani, Municipality | 659 | 586 | 470 | 108 | 437 | 31 | 2 | 116
113 | Kataiya, Town Panchayat | 690 | 574 | 459 | 71 | 441 | 11 | 7 | 115
114 | Baheri, Town Panchayat | 316 | 304 | 189 | 75 | 189 | 0 | 0 | 115
115 | Hathua, Town Panchayat | 168 | 145 | 33 | 101 | 33 | 0 | 0 | 112
116 | Basantpur, Town Panchayat | 187 | 178 | 69 | 106 | 69 | 0 | 0 | 109
117 | Maner, Town Panchayat | 445 | 233 | 126 | 104 | 111 | 15 | 0 | 107
118 | Champanagar, Town Panchayat | 529 | 458 | 353 | 104 | 353 | 0 | 0 | 105
119 | Teghra, Town Panchayat | 458 | 398 | 293 | 94 | 273 | 20 | 0 | 105
120 | Alamnagar, Town Panchayat | 2023 | 600 | 497 | 48 | 493 | 4 | 0 | 103
121 | Sheikhopur Sarai, Town Panchayat | 245 | 191 | 88 | 102 | 80 | 8 | 0 | 103
122 | Ghoghardiha, Town Panchayat | 160 | 160 | 59 | 85 | 52 | 7 | 0 | 101
123 | Kako, Town Panchayat | 233 | 185 | 88 | 93 | 88 | 0 | 0 | 97
124 | Sugauli, Town Panchayat | 307 | 268 | 171 | 86 | 160 | 1 | 10 | 97
125 | Madhubani, Municipal Corporation | 2417 | 619 | 523 | 96 | 497 | 25 | 1 | 96
126 | Nalanda, Town Panchayat | 572 | 519 | 424 | 88 | 405 | 19 | 0 | 95
127 | Rosera, Municipality | 889 | 249 | 156 | 86 | 109 | 46 | 1 | 93
128 | Bahadurganj, Town Panchayat | 363 | 333 | 240 | 76 | 232 | 8 | 0 | 93
129 | Habibpur, Town Panchayat | 745 | 602 | 510 | 89 | 371 | 139 | 0 | 92
130 | Bhawanipur, Town Panchayat | 347 | 240 | 148 | 90 | 148 | 0 | 0 | 92
131 | Mashrakh, Town Panchayat | 494 | 411 | 320 | 90 | 308 | 12 | 0 | 91
132 | Pawapuri, Town Panchayat | 648 | 472 | 384 | 80 | 321 | 63 | 0 | 88
133 | Bakhtiyarpur, Municipality | 179 | 117 | 29 | 88 | 28 | 1 | 0 | 88
134 | Jainagar, Town Panchayat | 358 | 256 | 169 | 55 | 134 | 35 | 0 | 87
135 | Nasriganj, Town Panchayat | 154 | 125 | 38 | 78 | 38 | 0 | 0 | 87
136 | Buxar, Municipality | 348 | 305 | 219 | 73 | 206 | 13 | 0 | 86
137 | Sursand, Town Panchayat | 1416 | 307 | 223 | 61 | 210 | 13 | 0 | 84
138 | Korha, Town Panchayat | 317 | 279 | 195 | 75 | 195 | 0 | 0 | 84
139 | Mairwa, Town Panchayat | 201 | 162 | 79 | 39 | 77 | 2 | 0 | 83
140 | Nirmali, Town Panchayat | 236 | 156 | 75 | 79 | 74 | 1 | 0 | 81
141 | Kursela, Town Panchayat | 228 | 212 | 131 | 81 | 110 | 21 | 0 | 81
142 | Bharwara, Town Panchayat | 792 | 535 | 455 | 68 | 408 | 47 | 0 | 80
143 | Karakat, Town Panchayat | 453 | 381 | 301 | 68 | 301 | 0 | 0 | 80
144 | Araria, Municipality | 207 | 106 | 27 | 79 | 26 | 1 | 0 | 79
145 | Rahui, Town Panchayat | 399 | 371 | 293 | 78 | 293 | 0 | 0 | 78
146 | Manihari, Town Panchayat | 148 | 112 | 36 | 76 | 36 | 0 | 0 | 76
147 | Nabinagar, Town Panchayat | 283 | 139 | 65 | 74 | 63 | 2 | 0 | 74
148 | Revelganj, Town Panchayat | 277 | 198 | 124 | 60 | 101 | 23 | 0 | 74
149 | Banmankhi Bazar, Municipality | 1397 | 228 | 156 | 66 | 156 | 0 | 0 | 72
150 | Haweli Kharagpur, Municipality | 320 | 274 | 202 | 64 | 192 | 10 | 0 | 72
151 | Khagaria, Municipality | 239 | 204 | 132 | 71 | 130 | 2 | 0 | 72
152 | Bagaha, Municipality | 815 | 677 | 606 | 69 | 516 | 10 | 80 | 71
153 | Gaya, Municipal Corporation | 1471 | 1227 | 1157 | 68 | 1129 | 17 | 11 | 70
154 | Mansi, Town Panchayat | 409 | 317 | 247 | 69 | 227 | 20 | 0 | 70
155 | Kanti, Municipality | 339 | 258 | 188 | 65 | 179 | 9 | 0 | 70
156 | Lalganj, Municipality | 303 | 214 | 145 | 66 | 111 | 34 | 0 | 69
157 | Akbarnagar, Town Panchayat | 420 | 350 | 281 | 63 | 230 | 51 | 0 | 69
158 | Tikari, Municipality | 403 | 384 | 315 | 68 | 312 | 3 | 0 | 69
159 | Singhia, Town Panchayat | 1075 | 901 | 833 | 63 | 822 | 11 | 0 | 68
160 | Baisi, Town Panchayat | 717 | 698 | 631 | 65 | 398 | 233 | 0 | 67
161 | Munger, Municipal Corporation | 301 | 292 | 225 | 64 | 197 | 12 | 16 | 67
162 | Asthawan, Town Panchayat | 865 | 741 | 675 | 65 | 663 | 12 | 0 | 66
163 | Koath, Town Panchayat | 323 | 294 | 228 | 63 | 129 | 78 | 21 | 66
164 | Chausa, Town Panchayat | 212 | 185 | 119 | 65 | 118 | 1 | 0 | 66
165 | Piro, Municipality | 325 | 187 | 122 | 63 | 94 | 28 | 0 | 65
166 | Jehanabad, Municipality | 338 | 258 | 193 | 64 | 175 | 17 | 1 | 65
167 | Warisaliganj, Town Panchayat | 270 | 195 | 130 | 59 | 66 | 63 | 1 | 65
168 | Jagdishpur, Town Panchayat | 521 | 233 | 169 | 35 | 149 | 19 | 1 | 64
169 | Naugachhia, Municipality | 386 | 199 | 135 | 41 | 111 | 22 | 2 | 64
170 | Hasanpura, Town Panchayat | 261 | 200 | 136 | 64 | 136 | 0 | 0 | 64
171 | Imamganj, Town Panchayat | 1532 | 616 | 553 | 59 | 551 | 2 | 0 | 63
172 | Kesaria, Town Panchayat | 200 | 181 | 120 | 58 | 96 | 24 | 0 | 61
173 | Chanpatia, Town Panchayat | 170 | 154 | 95 | 54 | 81 | 14 | 0 | 59
174 | Amdabad, Town Panchayat | 377 | 367 | 308 | 59 | 308 | 0 | 0 | 59
175 | Muzaffarpur, Municipal Corporation | 350 | 235 | 177 | 56 | 147 | 30 | 0 | 58
176 | Barbigha, Municipality | 436 | 370 | 314 | 52 | 282 | 32 | 0 | 56
177 | Supaul, Municipality | 275 | 198 | 143 | 53 | 132 | 11 | 0 | 55
178 | Barharia, Town Panchayat | 294 | 281 | 230 | 27 | 220 | 10 | 0 | 51
179 | Goraul, Town Panchayat | 812 | 541 | 491 | 37 | 473 | 17 | 1 | 50
180 | Daudnagar, Municipality | 1309 | 1132 | 1082 | 47 | 1076 | 6 | 0 | 50
181 | Pirpainti, Town Panchayat | 342 | 284 | 234 | 50 | 219 | 15 | 0 | 50
182 | Suryagadha, Municipality | 559 | 507 | 457 | 45 | 437 | 20 | 0 | 50
183 | Jamui, Municipality | 141 | 109 | 60 | 48 | 57 | 1 | 2 | 49
184 | Balrampur, Town Panchayat | 108 | 107 | 61 | 42 | 53 | 8 | 0 | 46
185 | Dhaka, Municipality | 135 | 135 | 89 | 223 | 72 | 9 | 8 | 46
186 | Barahiya, Municipality | 197 | 165 | 120 | 44 | 93 | 27 | 0 | 45
187 | Musri Gharari, Town Panchayat | 1569 | 655 | 612 | 41 | 474 | 138 | 0 | 43
188 | Guthani, Town Panchayat | 430 | 311 | 268 | 40 | 268 | 0 | 0 | 43
189 | Jhajha, Municipality | 876 | 723 | 681 | 41 | 649 | 30 | 2 | 42
190 | Bounsi, Town Panchayat | 596 | 529 | 487 | 40 | 439 | 48 | 0 | 42
191 | Kishanganj, Municipality | 325 | 102 | 61 | 41 | 57 | 4 | 0 | 41
192 | Dumraon, Municipality | 372 | 341 | 301 | 39 | 280 | 17 | 4 | 40
193 | Hilsa, Municipality | 218 | 218 | 178 | 42 | 154 | 21 | 3 | 40
194 | Bikram, Town Panchayat | 179 | 129 | 90 | 39 | 76 | 11 | 3 | 39
195 | Chandi, Town Panchayat | 85 | 85 | 46 | 39 | 46 | 0 | 0 | 39
196 | Sabour, Town Panchayat | 234 | 172 | 134 | 38 | 121 | 13 | 0 | 38
197 | Barsoi, Town Panchayat | 74 | 56 | 19 | 34 | 14 | 4 | 1 | 37
198 | Sultanganj, Municipality | 167 | 153 | 116 | 30 | 95 | 21 | 0 | 37
199 | Barh, Municipality | 118 | 115 | 78 | 27 | 62 | 16 | 0 | 37
200 | Kasba, Town Panchayat | 316 | 102 | 66 | 32 | 59 | 7 | 0 | 36
201 | Parbatta, Town Panchayat | 867 | 759 | 723 | 36 | 721 | 2 | 0 | 36
202 | Birpur, Town Panchayat | 213 | 104 | 69 | 34 | 65 | 4 | 0 | 35
203 | Katoria, Town Panchayat | 395 | 391 | 356 | 33 | 355 | 1 | 0 | 35
204 | Jamalpur, Municipality | 161 | 161 | 126 | 35 | 71 | 46 | 9 | 35
205 | Arwal, Municipality | 229 | 121 | 87 | 34 | 59 | 25 | 3 | 34
206 | Maharajganj, Town Panchayat | 240 | 117 | 84 | 20 | 84 | 0 | 0 | 33
207 | Tarapur, Town Panchayat | 352 | 338 | 305 | 32 | 262 | 43 | 0 | 33
208 | Murliganj, Town Panchayat | 165 | 128 | 97 | 31 | 92 | 5 | 0 | 31
209 | Dinara, Town Panchayat | 203 | 177 | 146 | 27 | 144 | 2 | 0 | 31
210 | Sheohar, Town Panchayat | 239 | 208 | 178 | 30 | 178 | 0 | 0 | 30
211 | Koilwar, Town Panchayat | 206 | 168 | 139 | 27 | 120 | 19 | 0 | 29
212 | Harnaut, Town Panchayat | 260 | 168 | 140 | 25 | 140 | 0 | 0 | 28
213 | Narkatiaganj, Municipality | 82 | 70 | 42 | 27 | 40 | 2 | 0 | 28
214 | Balia, Municipality | 268 | 75 | 48 | 27 | 48 | 0 | 0 | 27
215 | Sampatchak, Municipality | 124 | 122 | 96 | 24 | 47 | 49 | 0 | 26
216 | Jokihat, Town Panchayat | 249 | 239 | 214 | 12 | 212 | 1 | 1 | 25
217 | Dinapur Nizamat, Municipality | 131 | 129 | 104 | 22 | 83 | 21 | 0 | 25
218 | Saraiya, Town Panchayat | 512 | 412 | 388 | 23 | 384 | 4 | 0 | 24
219 | Mohania, Town Panchayat | 210 | 175 | 151 | 21 | 136 | 14 | 1 | 24
220 | Arrah, Municipal Corporation | 161 | 153 | 129 | 24 | 123 | 5 | 1 | 24
221 | Bikramganj, Municipality | 120 | 112 | 88 | 22 | 63 | 25 | 0 | 24
222 | Silao, Town Panchayat | 254 | 184 | 161 | 22 | 113 | 39 | 9 | 23
223 | Behea, Town Panchayat | 230 | 210 | 187 | 22 | 169 | 10 | 8 | 23
224 | Muraul, Town Panchayat | 200 | 181 | 158 | 23 | 145 | 13 | 0 | 23
225 | Ekangarsarai, Town Panchayat | 35 | 34 | 11 | 23 | 10 | 1 | 0 | 23
226 | Yogapatti, Town Panchayat | 415 | 393 | 371 | 19 | 354 | 17 | 0 | 22
227 | Forbesganj, Municipality | 109 | 104 | 82 | 21 | 73 | 8 | 1 | 22
228 | Paliganj, Town Panchayat | 107 | 88 | 67 | 20 | 65 | 2 | 0 | 21
229 | Aurangabad, Municipality | 221 | 213 | 192 | 20 | 141 | 51 | 0 | 21
230 | Khagaul, Municipality | 63 | 59 | 38 | 18 | 23 | 15 | 0 | 21
231 | Deo, Town Panchayat | 161 | 138 | 118 | 20 | 116 | 2 | 0 | 20
232 | Phulwari Sharif, Municipality | 64 | 61 | 41 | 20 | 37 | 3 | 1 | 20
233 | Andar, Town Panchayat | 107 | 72 | 53 | 19 | 53 | 0 | 0 | 19
234 | Kahalgaon, Town Panchayat | 245 | 188 | 170 | 16 | 96 | 74 | 0 | 18
235 | Chenari, Town Panchayat | 376 | 354 | 336 | 15 | 322 | 14 | 0 | 18
236 | Kudra, Town Panchayat | 228 | 209 | 191 | 16 | 184 | 7 | 0 | 18
237 | Sonepur, Town Panchayat | 100 | 87 | 69 | 17 | 60 | 8 | 1 | 18
238 | Shahpur, Town Panchayat | 94 | 90 | 72 | 17 | 51 | 16 | 5 | 18
239 | Barauni, Municipality | 557 | 472 | 457 | 2 | 457 | 0 | 0 | 15
240 | Asarganj, Town Panchayat | 161 | 149 | 134 | 15 | 111 | 23 | 0 | 15
241 | Mahnar Bazar, Municipality | 60 | 60 | 46 | 11 | 43 | 2 | 1 | 14
242 | Chewara, Town Panchayat | 181 | 98 | 85 | 13 | 85 | 0 | 0 | 13
243 | Beldaur, Town Panchayat | 320 | 310 | 297 | 12 | 296 | 1 | 0 | 13
244 | Khusrupur, Town Panchayat | 224 | 108 | 96 | 12 | 87 | 9 | 0 | 12
245 | Kurtha, Town Panchayat | 42 | 42 | 30 | 12 | 28 | 2 | 0 | 12
246 | Benipatti, Town Panchayat | 541 | 440 | 429 | 10 | 390 | 39 | 0 | 11
247 | Mokameh, Municipality | 126 | 24 | 14 | 9 | 11 | 3 | 0 | 10
248 | Kopa, Town Panchayat | 20 | 16 | 6 | 10 | 6 | 0 | 0 | 10
249 | Patna Municipal Corporation | 72 | 72 | 62 | 10 | 40 | 22 | 0 | 10
250 | Sikandra, Town Panchayat | 125 | 112 | 103 | 9 | 102 | 1 | 0 | 9
251 | Parbalpur, Town Panchayat | 46 | 42 | 33 | 9 | 33 | 0 | 0 | 9
252 | Brahmpur, Town Panchayat | 246 | 237 | 229 | 8 | 218 | 11 | 0 | 8
253 | Islampur, Municipality | 56 | 54 | 46 | 8 | 37 | 9 | 0 | 8
254 | Sarmera, Town Panchayat | 135 | 102 | 95 | 5 | 80 | 15 | 0 | 7
255 | Ramgarh, Town Panchayat | 170 | 145 | 141 | 4 | 138 | 3 | 0 | 4
256 | Rajgir, Town Panchayat | 99 | 89 | 85 | 4 | 56 | 29 | 0 | 4
257 | Chakia, Municipality | 1188 | 146 | 143 | 2 | 133 | 10 | 0 | 3
258 | Kochas, Town Panchayat | 61 | 2 | 0 | 2 | 0 | 0 | 0 | 2
259 | Rafiganj, Town Panchayat | 36 | 36 | 34 | 2 | 23 | 10 | 1 | 2
| Total | 175235 | 131175 | 83912 | 40916 | 77763 | 5661 | 488 | 47263